## Sheet1
UPdate IR Recommendations
Near Term | Status (10/2016)
1. Establish OPA as the recognized IR hub, with formal connections to other identified IR practitioners across campus, to consolidate duplication and add coherence to the dispersed IR effort. Connections may range from firmly established communication channels to dotted reporting lines. (Addresses process improvements: b, d, e, f, g) | Dotted lines in Student Success and HR established; regular meetings with SS, HR, Budget; Space planning and management function developed, in cooperation with OPA
2. Create a “community of practice” for IR professionals across the institution to create common definitions (in collaboration with data governance processes to be developed), coordinate on mutually beneficial projects, share tools and tricks of the trade, and share project outcomes. Group may grow over time as additional practitioners are identified and benefit of participation increases. There may be two groups – a core and an associated group. We recommend the core group meet weekly at least at the onset to develop momentum, with bi-weekly or monthly meetings of the associated group. (Addresses process improvements: d, e, f) | Tableau user group meets semi-regularly; College-level interest group proposed for 2016-17
3. Work with supervisors of IR professionals to formally share results more broadly. Where dotted reporting lines to OPA do not exist, this may include supervisors using results dissemination as an annual review criterion. (Addresses process improvements: a, b, c, e) | In progress, needs work
4. Establish a repository for shared results, likely using the OPA website initially, where results are appropriate for public or campus exposure. Explore options for alternative sharing access for sensitive results (based on individual level data or sensitive fields, e.g.). (Addresses process improvements: a, b, c, e) | Tableau Public and Server partially meet this recommendation
5. Propose incentives and remove barriers for faculty and graduate students to engage in IR, where it fits their scholarly agendas. This may include providing easy access to specified de-identified datasets for coursework and scholarship (using institutional repository to store and access datasets), appointing GRAs in offices that conduct IR work, or more in-depth collaboration on specific projects. (Addresses process improvements: a, c, g, h) | GA hired in OPA 2016-17; Datasets provided to students and faculty in Education, Agricultural Economics and Economics, Public Administration, other campuses
6. Create a “How do we find out…?” webpage to connect campus constituents with information sources across offices. (Addresses process improvements: a, b) | not completed
7. Engage IR professionals across campus in a workload and process assessment to determine baseline efficiency and effectiveness and inform decisions on position coordination and/or formal project queueing. (Addresses process improvements: d, e, f, g) | not started
8. Develop a strategy to inform campus about ongoing changes in where and how to obtain information. (Addresses process improvements: a, b) | informal campaign only
Long Term
1. Assess progress on access to information and analysis through user feedback, website hits, community of practice member feedback, and other qualitative and quantitative data (a, b) | internal assessment ongoing
2. Assess progress on coordination across community of practice through regular assessment of sessions and occasional formal solicitation of feedback from practitioners (Addresses process improvements: d, e, f) | internal assessment ongoing
3. Use workload and process assessment results along with coordination assessment to recommend additional reorganization of positions and reporting lines, if warranted (Addresses process improvements: d, e, f, g) | informal conversations with supervisors
4. Use workload and process assessment results to evaluate queueing/project management process. This may become an annual review. (Addresses process improvements: a, d, e, f, g) | not started
5. Propose and plan a major website overhaul to improve access and provide clarity for IR data. This would primarily impact OPA’s website but would include other places where IR reports or data are housed and accessed. (Addresses process improvements: a, b, h) | incremental website changes in OPA pages
6. Institute an annual MSU Institutional Research conference where diverse IR projects are presented to the larger MSU community. (Addresses process improvements: a, c, g, h) | Regional conference invitation extended to campus colleagues; OPA will be taking on/expanding ADVANCE charrette next year

## Sheet2
UPdate IR Desired Process Improvements
a. Improve access to information and analysis for decision making and scholarship
b. Provide clarity to university community about how to obtain information and analysis
c. Create a culture of data use and data quality expectations and assessment
d. Consolidate unnecessarily duplicative IR efforts
e. Improve collaboration, consistency, and accuracy for those conducting IR work
f. Improve efficiency and effectiveness of recurring IR tasks
g. Enable or encourage IR professionals to take on new strategic projects
h. Encourage faculty and graduate students to use institutional data sources for scholarly projects and institutional research ends